## Master
Chelan County Climate Resiliency Roundtable - DRAFT Work Plan
Small Committee | Key Action | Lead | Task Description | Priority | Deliverable | Resource Needed | Completion Date | 2023 - Q1 | 2023 - Q2 | 2023 - Q3 | 2023 - Q4 | 2024 - Q1 | 2024 - Q2 | 2024 - Q3 | 2024 - Q4 | Notes
Forest Health and Wildfire Resilience | Improve Forest Health and Wildfire Resiliency through development of resources that promote science-driven presciptions | TBD | Continue ongoing efforts to improve forest health and wildfire resiliency through thinning, Rx burning, managed wildfire, but increase emphasis on science-driven prescriptions that create more resilient landscapes in terms of climate change and increased moisture deficit/decreased snowpack. • Utilize emerging hydrologic modelling tools to prioritize treatments on a landscape to increase snowpack retention (aspect, forest type, treatment type, etc). Including clumps and gaps in treatment prescription is typically most beneficial for snowpack retention. • Emphasize ICO (Individual Clumps and Openings) treatment approach to mimic natural conditions and increase resiliency to drought and insect. • Focus on restoration of burned areas • Utilize moisture deficit modeling to apply treatments to shift forest structure in areas most vulnerable to drought (favor drought tolerant species in prescriptions) | 1 | Fact Sheet, NCWFHC Representative, Workshop, Courses |  | 2024-12-31 | Identify technical leads and resources needed to complete work plan | Work with DNR to develop a fact sheet for practitioners that can help guide the integration of snowpack retention priorities into landscape unit selection and prescriptions | Work with DNR to develop a fact sheet for practitioners that can help guide the integration of snowpack retention priorities into landscape unit selection and prescriptions | Identify representative at NCWFHC to keep messaging about the importance of incorporating unit prioritization and prescriptions for snowpack retention at the forefront. Disseminate fact sheet (partner with E&O Committee if needed) | Plan and hold workshop for foresters and practitioners to increase understanding of applications | Begin work to develop courses for loggers to help increase contractor understanding of prescriptions that promote snowpack retention goals (potentially through WSU extension) | Continue work to develop courses for loggers to help increase contractor understanding of prescriptions that promote snowpack retention goals (potentially through WSU extension) | Complete work to develop courses for loggers to help increase contractor understanding of prescriptions that promote snowpack retention goals (potentially through WSU extension) | Consensus: This will remain a priority for short term implementation, with the following actions identified as possible pathways toward implementation • Ongoing - Work with DNR (Derek Churchill, Chuck Hersey) to increase understanding about how this fits into the Forest Restoration Strategy update
Forest Health and Wildfire Resilience | Development of website/information hub | CCD | Support ongoing effort for the development of central website/information hub for public to access resources for increasing fire resiliency within communities, with a social media component. All agencies/entities will need to contribute information/links/updates. Our Valley Our Future: Our Valley Our Future Action Plan includes a Regional Wildfire Preparedness objective, including bilingual outreach and a plan to guide fire recovery efforts. | 2 | Website/ Communication Hub |  | 2023-12-31 | Identify technical leads and resources needed to complete work plan | Provide content/ support Regional Wildfire Preparedness objective | Provide content/ support Regional Wildfire Preparedness objective | Provide content/ support Regional Wildfire Preparedness objective |  |  |  |  | Consensus: This will remain a priority for short term implementation, with the understanding that it is already underway and the role of the Small Committee will be to continue to check in on the effort and see how different groups can support the effort and contribute to getting messaging spread broadly.
Water Resources | Water Resource Action Inventory | TBD | Conduct inventory of existing efforts going on within WR and identifying gaps and opportunities to fill from climate resiliency perspective | 1 | Gap Analysis | TBD | 2023-12-31 | Identify technical leads and resources needed to complete work plan | Identifying key partners/entities/orgs to gather information on ongoing efforts/current gaps | Conduct interviews and compile results into draft gap analysis | Finalize Gap Analysis and provide recommendations on which gaps are the most urgent and/or feasible to address |  |  |  |  | Gain a better understanding of what is happening and identify potential gaps for benefitting climate resiliency in water resource work.
Water Resources | Project Development and Funding Precurment | TBD | Scope and develop projects, programs, or activities that work to fill gaps identified in inventory effort, pursue funding for implementation | 2 | Project/Action List | TBD | TBD | Identify technical leads and resources needed to complete work plan | Gather information on current and future funding sources, may help refine project scoping | Gather information on current and future funding sources, may help refine project scoping | Support of Icicle Creek SnoTel site (being installed fall 2023) | Project/Program Scoping | Project/Program Development | Project/Program Development | Project/Program Development | Effort to identify p[rojects and programs that ensure water/snowpack are being considered and prioritized in habitat actions;evaluate with climate resiliency needs and priorities.
Public Health and Vulnerable Communities | Assessment to Identify Vulnerable Groups | TBD | Conduct vulnerability assessment, incorporating existing information, to quantify/identify who is at risk due to what climate stressors. Inventory resources available. | 1 | Vulnerability Assessment | TBD | 2023-12-31 | Identify technical leads and resources needed to complete work plan | Finalize methods for identifying vulnerable groups and information sources for assessment | Begin assessment and compile results into draft for review | Incorporate feedback from draft assessment and finalize
Public Health and Vulnerable Communities | Increase Information and Resources for Public Health Issues Specific to Vulerable Groups | TBD | Develop/curate outreach content, partnering with education/outreach committee. | 2 | PHVC Content | TBD | 2024-12-31 | Identify technical leads and resources needed to complete work plan | Pursue funding for events and to support labor/materials | Identify key stakeholders within vulnerable groups | Begin content development for vulnerable groups, vet through stakeholders, coordinate with E&O for 2023 events | Submit draft content to E&O committee to begin development of materials | Review draft E&O materials and provide feedback | Event planning/ participation for 2024 events, continue design | Work with E&O Committee to develop dissemination stategy
Education and Outreach | Stakeholder Engagement | TBD | Conduct a network analysis to identify stakeholders and cornerstone community members that have access to specific target audiences or groups | 1 | Memo compiling results from network analysis | Funding to support staff time | 2023-12-31 | Finalize technical leads for each target audience | Pursue funding and initate stakeholder engagement | Conduct interviews of key stakeholders | Complete Technical Memo
Education and Outreach | Information Dissemination | TBD | Utilize a variety of communication methods to build trust relationships, increase communications, and connect communities to resources and information | 2 | 2-3 specific outreach events or materials, TBD by outreach committee | Funding for development of outreach materials and labor for events | 2024-12-31 | Finalize techncial leads and list of events and outerach materials | Pursue funding, scope options for 2023 events | Event planning/ participation for 2023 events | Identify best outreach methods and mechanisms | Synthesis of content from other committees for outreach materials | Begin Design of Education and Outreach Materials | Event planning/ participation for 2024 events, continue design | Complete Design of Education and Outreach Materials

## Forest
Chelan County Climate Resiliency Roundtable - DRAFT Work Plan
Key Action | Lead | Task Description | Priority | Deliverable | Resource Needed | Completion Date | 2023 - Q1 | 2023 - Q2 | 2023 - Q3 | 2023 - Q4 | 2024 - Q1 | 2024 - Q2 | 2024 - Q3 | 2024 - Q4 | Notes
Improve Forest Health and Wildfire Resiliency through development of resources that promote science-driven presciptions | TBD | Continue ongoing efforts to improve forest health and wildfire resiliency through thinning, Rx burning, managed wildfire, but increase emphasis on science-driven prescriptions that create more resilient landscapes in terms of climate change and increased moisture deficit/decreased snowpack. • Utilize emerging hydrologic modelling tools to prioritize treatments on a landscape to increase snowpack retention (aspect, forest type, treatment type, etc). Including clumps and gaps in treatment prescription is typically most beneficial for snowpack retention. • Emphasize ICO (Individual Clumps and Openings) treatment approach to mimic natural conditions and increase resiliency to drought and insect. • Focus on restoration of burned areas • Utilize moisture deficit modeling to apply treatments to shift forest structure in areas most vulnerable to drought (favor drought tolerant species in prescriptions) | 1 | Fact Sheet, NCWFHC Representative, Workshop, Courses |  | 2024-12-31 | Identify technical leads and resources needed to complete work plan | Work with DNR to develop a fact sheet for practitioners that can help guide the integration of snowpack retention priorities into landscape unit selection and prescriptions | Work with DNR to develop a fact sheet for practitioners that can help guide the integration of snowpack retention priorities into landscape unit selection and prescriptions | Identify representative at NCWFHC to keep messaging about the importance of incorporating unit prioritization and prescriptions for snowpack retention at the forefront. Disseminate fact sheet (partner with E&O Committee if needed) | Plan and hold workshop for foresters and practitioners to increase understanding of applications | Begin work to develop courses for loggers to help increase contractor understanding of prescriptions that promote snowpack retention goals (potentially through WSU extension) | Continue work to develop courses for loggers to help increase contractor understanding of prescriptions that promote snowpack retention goals (potentially through WSU extension) | Complete work to develop courses for loggers to help increase contractor understanding of prescriptions that promote snowpack retention goals (potentially through WSU extension) | Consensus: This will remain a priority for short term implementation, with the following actions identified as possible pathways toward implementation • Ongoing - Work with DNR (Derek Churchill, Chuck Hersey) to increase understanding about how this fits into the Forest Restoration Strategy update
Development of website/information hub | CCD | Support ongoing effort for the development of central website/information hub for public to access resources for increasing fire resiliency within communities, with a social media component. All agencies/entities will need to contribute information/links/updates. Our Valley Our Future: Our Valley Our Future Action Plan includes a Regional Wildfire Preparedness objective, including bilingual outreach and a plan to guide fire recovery efforts. | 2 | Website/ Communication Hub |  | 2023-12-31 | Identify technical leads and resources needed to complete work plan | Provide content/ support Regional Wildfire Preparedness objective | Provide content/ support Regional Wildfire Preparedness objective | Provide content/ support Regional Wildfire Preparedness objective |  |  |  |  | Consensus: This will remain a priority for short term implementation, with the understanding that it is already underway and the role of the Small Committee will be to continue to check in on the effort and see how different groups can support the effort and contribute to getting messaging spread broadly.
Contractor Procurement | N/A | Address contractor shortage before it becomes a bottleneck in getting treatments done. Collaborate with agencies to provide educational courses for contractors on things like federal contracting and grant programs/agency agendas to give contractors the confidence to scale up at the appropriate times. Strategize amongst agencies on how to provide consistent funding to contractors to enable the scale-up. | N/A | Placeholder for future development | [10 empty] | This does not need to be a priority for implementation at this time, because there are other issues that need to be addressed first and this does not seem to be an issue currently. This issue may resolve itself as other issues are addressed.

## Water
Chelan County Climate Resiliency Roundtable - DRAFT Work Plan
Key Action | Lead | Task Description | Priority | Deliverable | Resource Needed | Completion Date | 2023 - Q1 | 2023 - Q2 | 2023 - Q3 | 2023 - Q4 | 2024 - Q1 | 2024 - Q2 | 2024 - Q3 | 2024 - Q4 | Notes
Water Resource Action Inventory | TBD | Conduct inventory of existing efforts going on within WR and identifying gaps and opportunities to fill from climate resiliency perspective | 1 | Gap Analysis | TBD | 2023-12-31 | Identify technical leads and resources needed to complete work plan | Identifying key partners/entities/orgs to gather information on ongoing efforts/current gaps | Conduct interviews and compile results into draft gap analysis | Finalize Gap Analysis and provide recommendations on which gaps are the most urgent and/or feasible to address |  |  |  |  | Gain a better understanding of what is happening and identify potential gaps for benefitting climate resiliency in water resource work.
Project Development and Funding Precurment | TBD | Scope and develop projects, programs, or activities that work to fill gaps identified in inventory effort, pursue funding for implementation | 2 | Project/Action List | TBD | TBD | Identify technical leads and resources needed to complete work plan | Gather information on current and future funding sources, may help refine project scoping | Gather information on current and future funding sources, may help refine project scoping | Support of Icicle Creek SnoTel site (being installed fall 2023) | Project/Program Scoping | Project/Program Development | Project/Program Development | Project/Program Development | Effort to identify p[rojects and programs that ensure water/snowpack are being considered and prioritized in habitat actions;evaluate with climate resiliency needs and priorities.

## PHVC
Chelan County Climate Resiliency Roundtable - DRAFT Work Plan
Key Action | Lead | Task Description | Priority | Deliverable | Resource Needed | Completion Date | 2023 - Q1 | 2023 - Q2 | 2023 - Q3 | 2023 - Q4 | 2024 - Q1 | 2024 - Q2 | 2024 - Q3 | 2024 - Q4 | Notes
Assessment to Identify Vulnerable Groups | TBD | Conduct vulnerability assessment, incorporating existing information, to quantify/identify who is at risk due to what climate stressors. Inventory resources available. | 1 | Vulnerability Assessment | TBD | 2023-12-31 | Identify technical leads and resources needed to complete work plan | Finalize methods for identifying vulnerable groups and information sources for assessment | Begin assessment and compile results into draft for review | Incorporate feedback from draft assessment and finalize
Increase Information and Resources for Public Health Issues Specific to Vulerable Groups | TBD | Develop/curate outreach content, partnering with education/outreach committee. | 2 | PHVC Content | TBD | 2024-12-31 | Identify technical leads and resources needed to complete work plan | Pursue funding for events and to support labor/materials | Identify key stakeholders within vulnerable groups | Begin content development for vulnerable groups, vet through stakeholders, coordinate with E&O for 2023 events | Submit draft content to E&O committee to begin development of materials | Review draft E&O materials and provide feedback | Event planning/ participation for 2024 events, continue design | Work with E&O Committee to develop dissemination stategy

## E&O
Chelan County Climate Resiliency Roundtable - Work Plan
Key Action | Lead | Task Description | Priority | Deliverable | Resource Needed | Completion Date | 2023 - Q1 | 2023 - Q2 | 2023 - Q3 | 2023 - Q4 | 2024 - Q1 | 2024 - Q2 | 2024 - Q3 | 2024 - Q4 | Notes
Stakeholder Engagement | TBD | Conduct a network analysis to identify stakeholders and cornerstone community members that have access to specific target audiences or groups | 1 | Tech Memo compiling results from network analysis | Funding to support staff time | 2023-12-31 | Finalize technical leads for each target audience | Pursue funding and initate stakeholder engagement | Conduct interviews of key stakeholders | Complete Technical Memo
Information Dissemination | TBD | Utilize a variety of communication methods to build trust relationships, increase communications, and connect communities to resources and information | 2 | 2-3 specific outreach events or materials, TBD by outreach committee | Funding for development of outreach materials and labor for events | 2024-12-31 | Finalize techncial leads and list of events and outerach materials | Pursue funding, scope options for 2023 events | Event planning/ participation for 2023 events | Identify best outreach methods and mechanisms | Synthesis of content from other committees for outreach materials | Begin Design of Education and Outreach Materials | Event planning/ participation for 2024 events, continue design | Complete Design of Education and Outreach Materials