## Sheet1
Planned and Completed Fuels Reduction Units in Stemilt-Squilchuck Planning Area August 2020
Unit | Acres | Type of Treatment | Land Ownership | Funding Source | Funding Amount | Status
2901 | 13 | PCT Hand Pile | County | USFS | 258272 | Complete 2018
2902 | 27.9 | PCT Lop and Scatter | County | USFS |  | Complete 2018
2903 | 10.7 | PCT Lop and Scatter | County | USFS |  | Complete 2018
2904 | 22.9 | Commercial Thin | County | USFS |  | Complete 2018
2905 | 20.8 | PCT Lop and Scatter | County | USFS |  | Complete 2018
2906 | 0.8 | PCT Hand Pile | County | USFS |  | Complete 2018
2907 | 72.6 | PCT Lop and Scatter | County | USFS |  | Complete 2018
2701 | 22.3 | PCT Hand Pile | County | USFS |  | Complete 2019
2702 | 29.1 | PCT Hand Pile | County | USFS |  | Complete 2019
2703 | 25.9 | PCT Lop and Scatter | County | USFS |  | Complete 2019
2704 | 57 | PCT Lop and Scatter | County | USFS |  | Complete 2019
Section 20 (Orr Creek) | 120 | Commercial Thin | WDFW | WDFW Capital | WDFW Capital | Complete 2019
Section 28 (Lily Lake) | 175.1 | Commercial Thin | WDFW | WDFW Capital |  | Complete 2019
Section 29 Prescribed Burn | 113 | Prescribed Burn | County | DNR 2018 | 63000 | Planned 2020
Section 27 Prescribed Burn | 57 | Prescribed Burn | County | DNR 2020 | 36712 | Planned 2020
Upper Wheeler SFB | 70 | PCT Lop and Scatter | WDFW | FEMA | 105181 | Planned 2021
Mission/Forest Ridge | 64 | PCT Hand Pile | Private | FEMA | 93409 | Planned 2021
Scout-A-Vista | 29 | PCT | Private | FEMA | 136300 | Planned 2021
Squilchuck State Park | 48 | Commercial Thin | State Parks | State Parks Capital | State Parks Capital | Complete 2019
Section 19/30 Mission Ridge | 171 | Commercial Thin | Private | Private funding | Private Funding | Planned 2020
Section 13A | 98 | Post-Comm Thin | Private | DNR 2020 | 56490 | Planned 2020
Section 13B | 23 | PCT Lop and Scatter | Private | DNR 2020 |  | Planned 2020
USFS Mission Maint. | 592 | Prescribed Burn | USFS | USFS | USFS Capital | Planned 2021
Section 1 | 105 | PCT Lop and Scatter | County | DNR 2020 | 69990 | Planned 2020
County Section 23 + Additional Acreage TBD | 515 | Commercial Thin/PCT Lop and Scatter | County, Private | USFS LSR | 293000 | Planned 2022
Total | 2483.1 |  |  |  | 1112354
funded by DNR All Lands 2020
funded by DNR Cross Boundary 2018 (layout of 400 acres including the FEMA units also funded by DNR 2018)
Additional Funding Leveraged for Stemilt-Squilchuck Planning Area |  |  |  |  | Total Amount Leveraged: $1,272,610
Item |  | Funding Amount | Source
Landscape Evaluation |  | 30338 | USFS
Chelan County Lands Forest Management Plan |  | 55550 | USFS
DNR Small Forest Landowner Program 50% Cost Share for work on Section 13 |  | 64368 | DNR Small Landowner Program
Monitoring/Treatment Tracking |  | 10000 | USFS LSR
Total |  | 160256

## Sheet2
Planned Fuels Reduction Units in Stemilt-Squilchuck Planning Area March 2020
Unit | Acres | Type of Treatment | Ownership | Funding Source | Status | Landonwer Agreement
Section 29 Prescribed Burn | 113 | Prescribed Burn | County | DNR 2018 | Planned 2020 | Planned for implementation with partners aligned
Section 27 Prescribed Burn | 57 | Prescribed Burn | County | DNR 2020 | Planned 2020 | Same as above
Upper Wheeler SFB | 70 | PCT Lop and Scatter | WDFW, Private | FEMA | Planned 2021 | Letter of support from WDFW, private agreement pending
Mission/Forest Ridge | 30 | PCT Hand Pile | Private | FEMA | Planned 2021 | Letter of support from Tamarack Saddle
Scout-A-Vista | 50 | PCT | Private | FEMA | Planned 2020 | Planned by Cascadia
Section 13A | 98 | Post-Comm Thin | Private | DNR 2020 | Planned 2020 | Planning in collaboration with CCNRD and DNR, agreement implied
Section 13B | 23 | PCT Lop and Scatter | Private | DNR 2020 | Planned 2020 | Same as above
USFS Mission Maint. | 592 | Prescribed Burn | USFS | USFS | Planned 2021 | In USFS 2020 workplan
Section 1 | 125 | PCT Lop and Scatter | County | DNR 2020 | Planned 2020 | Planned by County
Sections 9, 5, 31, 23 |  | Wildlife Habitat Tx | WDFW | WDFW, RMEF | Planning Stage | WDFW verbal interest as of March 2020
Section 23, 26 |  | Commercial, Burn | County | LSR | Planning Stage | Planned as focus area by County for layout in 2020
Section 4, 6, 8, 32 |  | Commercial, PCT | DNR | DNR | Planning Stage | Planned by DNR, verbal agreement to work with WDFW and County to identify cross-boundary treatment opportunites
Section 9 |  | Commercial, PCT | Private | LSR | Planning Stage | Verbal interest, written agreement pending
Total | 1158
funded by DNR All Lands 2020
funded by DNR All Lands 2018 (layout of 400 acres also funded by DNR 2018)